## Slide 1: 10 steps to Trauma Aware and Healing Informed Residential Aged Care for Forgotten Australians and careleavers

## Slide 2: 1. Getting started 2. Engage the local leadership team and find champions 3. Engage staff and start training 4. Connect with local care leaver support service 5. Document review and set approach 6. Creating a positive resident experience 7. Planning a launch event 8. Embedding your program 9. Seek specialisation verification 10. Seek feedback and embed learnings
1-4
5
6-9
10
10
11
12
13-22
24
Week
23

## Slide 3: Getting started Have the initial conversations within the leadership and staff teams, prepare to seek formal approval as required, undertake project planning and familiarise yourself with the Real Care the Second Time Around materials i.
Week 1-4

## Slide 4: Supporting materials i. Slide deck - introduction to trauma informed residential aged care for Forgotten Australians and care leavers ii. Board briefing template i.
Week 1-4

## Slide 5: 2. Engage leadership team and find champions Set aside 3 hours with your leadership team – you will go through the leadership workshop and work out what this means for everyone and how you are going to proceed, who will be the Champions and how you will engage your teams
Week 5

## Slide 6: Supporting materials i. Champion role description ii. Leadership workshop slide deck
Week 5

## Slide 7: 3. Engage staff and start training Bringing the staff on board – from hospitality to clinical – is key to success. In this phase you will let staff know what is happening, who you require to do the training, then bring it to life through debriefing and team meetings over the coming months. Decide who will be required to do the training and by when. Make sure they feel supported as this topic can raise strong emotions. Maybe you establish a reference or advisory group. Inform residents and families about what you are doing by sharing fact sheets with them. Training module 1 is trauma awareness training suitable for all staff. Training module 2 is aimed at intake and lifestyle planning staff.
Week 6-9

## Slide 8: Supporting materials i. Baseline staff awareness survey ii. Online training module 1 – Trauma training iii. Online training module 2 – Sensitive conversations iv. Debrief guide v. Terms of reference for advisory group vi. Resident fact sheet vii. Community fact sheet viii. Staff fact sheet
Week 6-9

## Slide 9: 4. Connect with local care leaver support service Careleaver support services operate across the country and are experts in working with Forgotten Australians and careleavers. Connect with your local service, invite them to address the team and make sure you all know how to refer a resident to them. Maybe you have some brochures or information available. Formalise the arrangement with a MOU or letter.
Week 10

## Slide 10: Supporting materials i. List of careleaver support services Support Services | Find and Connect ii. MOU template
Week 10

## Slide 11: 5. Document review and set approach What documentation needs to be reviewed to embed trauma informed care and how will you formalise your approach into business as usual? Some suggestions follow
Week 10

## Slide 12: Supporting material i. Staff induction material paragraphs ii. Trauma informed aged care policy/ statement of commitment template iii. Visitor fact sheet – trauma informed care
Week 10

## Slide 13: 6. Creating a positive resident experience How will residents experience trauma aware and healing informed care? In this phase you will ensure there is information about your approach in your information material and on your website, you will provide opportunities for people to disclose a care history at intake and in lifestyle planning, you will have material accessible from care leaver services where someone does disclose, and you will think about marking days of significance for Forgotten Australians and care leavers. Check to make sure that building names are not adding to trauma.
Week 11

## Slide 14: Supporting material i. Calendar of significant days ii. Diversity intake form iii. Information for new or prospective residents
Week 11

## Slide 15: 7. Planning for launch A launch is optional but it is a great opportunity to create momentum, bring in your staff and residents and to connect with your broader community on trauma aware and healing informed care. i.
Week 12

## Slide 16: Supporting materials i. Community fact sheet ii. Resident fact sheet iii. Launch program draft
Week 12

## Slide 17: 8. Embedding your program Run weekly toolkit sessions with your teams. Include updates on your actions in newsletters and communications with residents, families and staff. Maybe have a standing agenda item in team meetings
Week 13-22

## Slide 18: 8. Embedding your program i. Team talk tools
Week 13-22

## Slide 19: 9. Seek specialisation verification Verification of care leaver specialisation is important for when people are looking for appropriate supports. Now that you have put all the pieces in place, you should consider applying.
Week 23

## Slide 20: Supporting material i. Link to verification information https://www.health.gov.au/topics/aged-care/providing-aged-care-services/reporting/specialisation-verification-framework
Week 23

## Slide 21: 10. Seek feedback and embed learnings Find out the impact you have had by running a post roll out staff survey. Review your model of care and embed the learning from the last six months into your daily care and service delivery
Week 24

## Slide 22: 10. Post training staff survey
Week 24